## How to use
MSP Client Onboarding Checklist
8 phases, 76 tasks, in dependency order.
Save a copy per client. Delete rows that do not apply at kickoff, but keep the phase
structure identical across clients so a technician always knows where they are.
Status has a dropdown. Filter the header row to see what is open or blocked.
Phase summaries
1. Pre-kickoff discovery (owner: Technical lead, with the client's IT champion)
Everything here should arrive on a questionnaire before anyone drives to a site. Discovery gaps are what turn a fixed-fee onboarding into an overrun.
2. Contract and scope confirmation (owner: Account owner)
Discovery usually changes the numbers the proposal was built on. Reconcile the commercial terms against what you actually found before the technical work starts.
3. Credential and admin tenant handover (owner: Senior engineer, with a second engineer verifying)
The phase that stalls most often, and the one where a missed step leaves you unable to fix something at 2am. Nothing here belongs in a ticket, an email thread, or a spreadsheet.
4. RMM and endpoint agent deployment (owner: Deployment engineer)
Deployment is not finished when the installer runs. It is finished when the installed count reconciles against the discovery inventory twice.
5. Backup and continuity verification (owner: Backup or infrastructure engineer)
You inherited a backup configuration. Until something restores, you have not inherited a recovery capability. Do this inside onboarding, while the client still expects the disruption.
6. Documentation capture (owner: Whoever performed the work, reviewed by the technical lead)
Documentation written during onboarding is accurate. Documentation written six months later is archaeology. Capture it as each phase finishes rather than as a final task.
7. User communication and rollout (owner: Account owner, with the client's leadership fronting it)
The client's staff did not choose you and mostly did not know this was happening. What they experience in week one sets how they talk about you internally for a year.
8. First 30 days review (owner: Account owner plus the technical lead)
The step most often skipped, and the one that catches everything discovery missed while the client still considers it part of onboarding rather than a complaint.
Full guide: https://pathalize.com/blog/msp-client-onboarding-checklist

## Checklist
Phase | # | Task | Phase owner | Status | Assigned to | Due date | Notes
1. Pre-kickoff discovery | 1.1 | Endpoint count by type: workstations, laptops, physical servers, hypervisors and guest VMs, mobile devices in scope | Technical lead, with the client's IT champion | Not started
1. Pre-kickoff discovery | 1.2 | Identity platform and topology: Microsoft Entra ID, on-premises Active Directory, hybrid with Entra Connect, or Google Workspace, and which directory is authoritative | Technical lead, with the client's IT champion | Not started
1. Pre-kickoff discovery | 1.3 | Every SaaS tenant you will be asked to administer, with the account that currently holds global admin on each | Technical lead, with the client's IT champion | Not started
1. Pre-kickoff discovery | 1.4 | Network hardware: firewall make, model, and firmware, switch stack, wireless controller, and any site-to-site tunnels | Technical lead, with the client's IT champion | Not started
1. Pre-kickoff discovery | 1.5 | ISP circuits with account numbers, contract end dates, and static IP assignments | Technical lead, with the client's IT champion | Not started
1. Pre-kickoff discovery | 1.6 | Current backup product, what it covers, retention, where the copies live, and the date of the last verified restore | Technical lead, with the client's IT champion | Not started
1. Pre-kickoff discovery | 1.7 | Line-of-business applications with vendor, support contract, and the internal person who actually owns each one | Technical lead, with the client's IT champion | Not started
1. Pre-kickoff discovery | 1.8 | Existing security tooling: EDR or antivirus product, MFA coverage percentage, email filtering, DNS filtering | Technical lead, with the client's IT champion | Not started
1. Pre-kickoff discovery | 1.9 | Compliance obligations in scope: HIPAA, PCI DSS, CMMC, SOC 2, or cyber insurance control requirements | Technical lead, with the client's IT champion | Not started
1. Pre-kickoff discovery | 1.10 | The outgoing provider, their contract end date, and whether they have been told yet | Technical lead, with the client's IT champion | Not started
1. Pre-kickoff discovery | 1.11 | Anything explicitly out of scope, written down before kickoff rather than argued about after the first ticket | Technical lead, with the client's IT champion | Not started
2. Contract and scope confirmation | 2.1 | Signed MSA and SOW on file with the service catalog attached | Account owner | Not started
2. Contract and scope confirmation | 2.2 | Covered device and user counts agreed, with the true-up mechanism and the review date written down | Account owner | Not started
2. Contract and scope confirmation | 2.3 | SLA tiers defined: severity levels, initial response targets, resolution targets, and coverage hours, in the client's language rather than your internal shorthand | Account owner | Not started
2. Contract and scope confirmation | 2.4 | After-hours and emergency rates agreed, so the first weekend incident is not a pricing conversation | Account owner | Not started
2. Contract and scope confirmation | 2.5 | Named client-side decision maker plus a technical champion authorized to approve changes | Account owner | Not started
2. Contract and scope confirmation | 2.6 | Escalation path handed over in writing, in both directions, before anyone needs it | Account owner | Not started
2. Contract and scope confirmation | 2.7 | Onboarding project fee and timeline quoted separately from the recurring fee | Account owner | Not started
2. Contract and scope confirmation | 2.8 | Letters of authorization signed for ISP, registrar, and vendor account changes | Account owner | Not started
2. Contract and scope confirmation | 2.9 | Data handling, confidentiality, and breach notification terms reviewed if the client is regulated | Account owner | Not started
2. Contract and scope confirmation | 2.10 | Offboarding and data-return terms agreed now, while the relationship is new | Account owner | Not started
3. Credential and admin tenant handover | 3.1 | Global admin or delegated admin access granted on every tenant in scope: Microsoft 365, Entra, Azure subscriptions, Google Workspace | Senior engineer, with a second engineer verifying | Not started
3. Credential and admin tenant handover | 3.2 | Break-glass account created, excluded from conditional access, credentials sealed and stored separately from the working set | Senior engineer, with a second engineer verifying | Not started
3. Credential and admin tenant handover | 3.3 | Domain registrar and DNS access confirmed, with the current zone exported and saved before anything is changed | Senior engineer, with a second engineer verifying | Not started
3. Credential and admin tenant handover | 3.4 | Firewall, switch, and wireless controller admin credentials rotated to accounts you control, vendor default accounts disabled | Senior engineer, with a second engineer verifying | Not started
3. Credential and admin tenant handover | 3.5 | Hypervisor, server local admin, and out-of-band management credentials captured and rotated | Senior engineer, with a second engineer verifying | Not started
3. Credential and admin tenant handover | 3.6 | Backup console access confirmed under an account you own rather than an account the outgoing provider owns | Senior engineer, with a second engineer verifying | Not started
3. Credential and admin tenant handover | 3.7 | CSP relationship, partner of record, and vendor billing ownership transferred where the contract says they should be | Senior engineer, with a second engineer verifying | Not started
3. Credential and admin tenant handover | 3.8 | Every credential filed in your password manager or documentation platform against the client record, with MFA enrolled on each administrative account you now hold | Senior engineer, with a second engineer verifying | Not started
3. Credential and admin tenant handover | 3.9 | The outgoing provider's remaining access enumerated, with a removal date scheduled rather than executed immediately | Senior engineer, with a second engineer verifying | Not started
3. Credential and admin tenant handover | 3.10 | A written list of any credential you could not obtain, what it blocks, and the recovery path with an owner and a date | Senior engineer, with a second engineer verifying | Not started
4. RMM and endpoint agent deployment | 4.1 | Client site or tenant created in the RMM first, with the correct policy group, so no agent lands in a default bucket | Deployment engineer | Not started
4. RMM and endpoint agent deployment | 4.2 | RMM agent deployed by GPO, Intune, or scripted install, then reconciled against the discovery endpoint count | Deployment engineer | Not started
4. RMM and endpoint agent deployment | 4.3 | EDR or antivirus deployed, with the previous product fully uninstalled rather than left dormant and conflicting | Deployment engineer | Not started
4. RMM and endpoint agent deployment | 4.4 | Backup agents deployed and every protected workload confirmed to be assigned to a live job, not just licensed | Deployment engineer | Not started
4. RMM and endpoint agent deployment | 4.5 | Patch policy applied with maintenance windows the client approved in writing | Deployment engineer | Not started
4. RMM and endpoint agent deployment | 4.6 | Monitoring thresholds configured: disk, memory, service checks, certificate expiry, backup job failure, and offline endpoint | Deployment engineer | Not started
4. RMM and endpoint agent deployment | 4.7 | Alerts routed into your PSA with the correct client mapping, so tickets land against the right account from day one | Deployment engineer | Not started
4. RMM and endpoint agent deployment | 4.8 | Remote access tested on every endpoint, including the laptops that were not in the building during rollout | Deployment engineer | Not started
4. RMM and endpoint agent deployment | 4.9 | Endpoint count reconciled a second time after seven days, because machines that were powered off during rollout are the ones that break your inventory | Deployment engineer | Not started
4. RMM and endpoint agent deployment | 4.10 | Outgoing provider's agents removed once yours are reporting cleanly | Deployment engineer | Not started
5. Backup and continuity verification | 5.1 | Every server, workstation set, and SaaS tenant in scope confirmed to be covered by a defined job | Backup or infrastructure engineer | Not started
5. Backup and continuity verification | 5.2 | SaaS backup handled separately, since Microsoft 365 and Google Workspace retention is not a backup you can restore from on your terms | Backup or infrastructure engineer | Not started
5. Backup and continuity verification | 5.3 | Retention configured to match what the contract promised rather than what the previous provider left behind | Backup or infrastructure engineer | Not started
5. Backup and continuity verification | 5.4 | A real test restore performed: one file, one mailbox item, and one full VM if the client has virtualized workloads | Backup or infrastructure engineer | Not started
5. Backup and continuity verification | 5.5 | RPO and RTO documented per workload and acknowledged by the client in writing | Backup or infrastructure engineer | Not started
5. Backup and continuity verification | 5.6 | At least one copy held outside the production environment, immutable if the product supports it | Backup or infrastructure engineer | Not started
5. Backup and continuity verification | 5.7 | Backup failure alerting routed somewhere a person reads daily, not to a shared mailbox nobody opens | Backup or infrastructure engineer | Not started
5. Backup and continuity verification | 5.8 | Restore procedure written where an on-call engineer can follow it without calling anyone | Backup or infrastructure engineer | Not started
6. Documentation capture | 6.1 | Network diagram covering circuits, firewall, VLANs, switch stack, wireless, and any site-to-site connectivity | Whoever performed the work, reviewed by the technical lead | Not started
6. Documentation capture | 6.2 | Server and workload inventory with role, operating system, patch state, dependencies, and application owner | Whoever performed the work, reviewed by the technical lead | Not started
6. Documentation capture | 6.3 | Identity documentation: domains, sync topology, conditional access policies, and license entitlement counts | Whoever performed the work, reviewed by the technical lead | Not started
6. Documentation capture | 6.4 | Application list with vendor, support contact, contract number, and renewal date | Whoever performed the work, reviewed by the technical lead | Not started
6. Documentation capture | 6.5 | Runbooks for the client's unusual or recurring procedures, including the ones with no modern replacement | Whoever performed the work, reviewed by the technical lead | Not started
6. Documentation capture | 6.6 | Vendor contact list with account numbers and the authorization each vendor requires before they will talk to you | Whoever performed the work, reviewed by the technical lead | Not started
6. Documentation capture | 6.7 | Renewal calendar for licenses, warranties, circuits, certificates, and domain expiry | Whoever performed the work, reviewed by the technical lead | Not started
6. Documentation capture | 6.8 | Standard operating procedures for anything a new technician would otherwise have to interrupt someone to ask about | Whoever performed the work, reviewed by the technical lead | Not started
6. Documentation capture | 6.9 | A scheduled review date, because the gap between the documentation and the environment is what makes year two harder than year one | Whoever performed the work, reviewed by the technical lead | Not started
7. User communication and rollout | 7.1 | Announcement sent by the client's leadership rather than by you, because adoption follows their authority | Account owner, with the client's leadership fronting it | Not started
7. User communication and rollout | 7.2 | Service desk contact routes published: portal, email address, and phone number, with what each one is for | Account owner, with the client's leadership fronting it | Not started
7. User communication and rollout | 7.3 | Severity definitions and response targets published in plain language | Account owner, with the client's leadership fronting it | Not started
7. User communication and rollout | 7.4 | A short live or recorded session covering the new support process and what changes for users | Account owner, with the client's leadership fronting it | Not started
7. User communication and rollout | 7.5 | Direct escalation route given to the office manager or IT champion before they need it | Account owner, with the client's leadership fronting it | Not started
7. User communication and rollout | 7.6 | Expectations set for the visible changes: MFA prompts, new agents, password policy, and patch reboots | Account owner, with the client's leadership fronting it | Not started
7. User communication and rollout | 7.7 | VIP handling confirmed if the client has executives with different expectations | Account owner, with the client's leadership fronting it | Not started
7. User communication and rollout | 7.8 | Out-of-hours contacts collected for the people authorized to approve emergency work | Account owner, with the client's leadership fronting it | Not started
7. User communication and rollout | 7.9 | The client's decision maker given a live view of onboarding progress, so status is something they check rather than something they request | Account owner, with the client's leadership fronting it | Not started
8. First 30 days review | 8.1 | Device and user counts reconciled against the contract and billing trued up | Account owner plus the technical lead | Not started
8. First 30 days review | 8.2 | First month of tickets reviewed by category, since early ticket themes are a direct readout of what discovery missed | Account owner plus the technical lead | Not started
8. First 30 days review | 8.3 | Every backup job confirmed to have succeeded and been verified at least once since deployment | Account owner plus the technical lead | Not started
8. First 30 days review | 8.4 | Patch cycle confirmed to have run, with reboot compliance where you expect it | Account owner plus the technical lead | Not started
8. First 30 days review | 8.5 | Every remediation item from discovery either closed or converted into a dated project with a named owner | Account owner plus the technical lead | Not started
8. First 30 days review | 8.6 | Outgoing provider access confirmed fully revoked and their agents confirmed removed | Account owner plus the technical lead | Not started
8. First 30 days review | 8.7 | Thirty-day review held with the client's decision maker: what went well, what is still open, what the roadmap looks like | Account owner plus the technical lead | Not started
8. First 30 days review | 8.8 | First monthly report date and first QBR scheduled before the review call ends | Account owner plus the technical lead | Not started
8. First 30 days review | 8.9 | Anything you had to correct during this onboarding fed back into the template so the next client starts from the corrected version | Account owner plus the technical lead | Not started